## UI-test case
TC# | Scenario | Title | Steps | Expected Result | Status | Comments | SMOKE TEST CANDIDATE
1 | User Registration | User Registration-valid credentials | 1. Go to https://thinking-tester-contact-list.herokuapp.com/ 2. Verify page title "Contact List App" 3.Click on "Sign Up" button 4.Verify page title "Add User" 5.Enter valid user details (f.name(Test), l.name(Tester),email(majamkaran+123@gmail.com), password(ABC1234)) 6.Click "Submit" button | User see confimation message "Registration successful. Please check your email for confirmation" | Fail | Positive Bug#1 | TRUE
2 |  | User registration- different valid email formats | Preconditions: User is on the Sign-Up page. 1.Enter First Name: Test,Enter Last Name: Tester 2. Enter different email formats: - fakeemail987@test.com -fakeemail234@gmail.co.uk - fakeEmailR5@gmail.io 5. Enter Password: ABC1234 6.Click "Submit" button | User is registered successfully with each valid email format. Confimation message "Registration successful. Please check your email for confirmation" is shown after each registration. | Fail | Positive | Not a smoke test, but I automate it out of curiosity
3 |  | User Registration-Invalid password | Preconditions: User is on the Sign-Up page. 1.Enter valid user details (f.name(Test), l.name(Tester),email(majamkaran+123@gmail.com), password(ABC123)) 2.Click "Submit" button | Error message appears "User validation failed: password: Path `password` (`ABC123`) is shorter than the minimum allowed length (7)." | Pass | Negative/Boundary
4 |  | User Registration-Invalid email | Preconditions: User is on the Sign-Up page. 1.Enter valid user details (f.name(Test), l.name(Tester),email(majamkaran+123.com), password(ABC1234)) 2.Click "Submit" button | Error message appears "User validation failed: email: Email is invalid" | Pass | Negative
5 |  | User Registration- "First Name" field left blank | Preconditions: User is on the Sign-Up page. 1.Enter user details ( l.name(Tester),email(majamkaran+123gmail.com), password(ABC1234)) 2.Click "Submit" button | Error message appears "User validation failed: firstName: Path `firstName` is required." | Pass | Negative
6 |  | User Registration- User is unable to use already registared email | Preconditions: User is on the Sign-Up page. Email is already registered. 1.Enter user details ( l.name(Tester),email(majamkaran+1gmail.com), password(ABC1234)) 2.Click "Submit" button | Error message appears "Email address is already in use" | Pass | Negative
7 |  | User Registration- "Cancel" button functionality | Preconditions: User is on the Sign-Up page. 1.Enter user details ( f.name(Test),l.name(Tester),email(majamkaran+123gmail.com), password(ABC1234)) 2.Click "Cancel" button | User redirected to Log In page and action is canceled without creating an account | Pass | Positive
8 | Login Functionality | Login with Valid Credentials | Preconditions: The user has an existing account. 1. Go to https://thinking-tester-contact-list.herokuapp.com/ 2. Verify page title "Contact List App" 3.Enter valid email into Email field (majamkaran+123@gmail.com) 4. Enter valid password into Password field (ABCE1234) 5. Click On "Submit" button | The user is successfully logged in and redirected to the home/dashboard page | Pass | Positive | TRUE
9 |  | Login with Incorrect Password | Preconditions: The user has an existing account. User is on the Log In page. 1.Enter valid email into Email field (majamkaran+123@gmail.com) 2. Enter invalid password into Password field (ABCE1234) 3. Click On "Submit" button | The system displays an error message "Incorrect username or password". The user remains on the Login page. | Pass | Negative Suggesting a different error message: Incorrect password. Please try again
10 |  | Login with Incorrect Email | Preconditions: The user has an existing account. User is on the Log In page. 1.Enter invalid email (majamkaran+123@gmai.com) 2. Enter valid password (ABC1234) 3. Click On "Submit" button | The system displays an error message "Incorrect username or password". The user remains on the Login page. | Pass | Negative Suggesting a different error message: Incorrect Email. Please try again
11 |  | Login with Unregistered Email | Preconditions: User is on the Log In page. 1.Enter email that is not registered (majamkaran+9@gmail.com) 2. Enter valid password (ABC1234) 3. Click On "Submit" button | The system displays an error message "Incorrect username or password". | Pass | Negative Suggesting a different error message: No account found with this email
12 |  | Login with Empty Email Field | Preconditions: The user has an existing account. User is on the Log In page. 1.Leave the Email field empty 2. Enter valid password (ABC1234) 3. Click On "Submit" button | The system displays an error message "Incorrect username or password". The user remains on the Login page. | Pass | Negative Suggesting a different error message: Email is required
13 |  | Login with Empty Password Field | Preconditions: The user has an existing account. User is on the Log In page. 1.Enter valid email (majamkaran+123@gmail.com) 2. Leave the Password field empty 3. Click On "Submit" button | The system displays an error message "Incorrect username or password". The user remains on the Login page. | Pass | Negative Suggesting a different error message: Password is required
14 |  | Login with Invalid Email Format | Preconditions: The user has an existing account. User is on the Log In page. 1.Enter valid email (majamkaran+123@.com) 2. Enter valid password (ABC1234) 3. Click On "Submit" button | The system displays an error message "Incorrect username or password". The user remains on the Login page. | Pass | Negative Suggesting a different error message: Please enter a valid email address
15 |  | Password Field Allows Only Hidden Input | Preconditions: The user has an existing account. User is on the Log In page. 1.Enter a password in the Password field. 2.Observe if the characters are hidden (displayed as dots). | The password is hidden by default. | Pass | Positive
16 | Login Session Timeout | Verify that an inactive user session times out after a set period | Preconditions: User is on the Log In page. 1.Log in with valid credentials(email:majamkaran+123@gmail.com), pass:ABC1234) 2.Stay inactive for the system-defined session timeout period. 3.Try to access a page after the timeout. | The system should log the user out and redirect them to the Login page. | N/A | Positive
17 | Logout Functionality | Verify that the logout functionality works correctly | Preconditions: User is on the Log In page. 1.Log in with valid credentials(email:majamkaran+123@gmail.com), pass:ABC1234) 2.Click the Logout button. | The user should be redirected to the Login page after logout. The session should be terminated. | Pass | Positive | TRUE
18 | Add Contact Functionality | Verify contact is added- valid data for all fields | Preconditions: User is logged in. 1. Click on "Add a New Contact" button 2.Enter valid credentials (F. Name:Peter, L. Name:Smith, DOB:1980-10-11, Email:peters@fake.com, Phone:7737894321, Street Address 1:Main St, Street Address 2:Apt 3, City:Chicago, State of Province:IL, Postal Code:34638, Country:USA 3. Click "Submit" button | Contact is successfully added to the system. User is redirected to "Contact list" page. | Pass | Positive | TRUE
19 |  | Verify contact can be created filling only mandatory fields | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter only mandatory fields(F.Name:Dan, L.Name:Danish) 3.3. Click "Submit" button | Contact is successfully added to the system. User is redirected to "Contact list" page. | Pass | Positive
20 |  | Verify contact can not be created leaving mandatory field empty | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter F.Name:Dan, leave L.Name empty) 3.3. Click "Submit" button | Error message apperas "Contact validation failed: lastName: Path `lastName` is required." | Pass | Negative
21 |  | Verify DOB field do not accept different valid format (mm/dd/yyyy) | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter mandatory fields(F.Name:Dan, L.Name:Danish) 3.Enter DOB:/10/26/1983 4.3. Click "Submit" button | Error message appears "Contact validation failed: birthdate: Birthdate is invalid" | Pass | Negative
22 |  | Verify DOB field accept different valid format (yyyy/mm/dd) | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter mandatory fields(F.Name:Dan, L.Name:Danish) 3.Enter DOB:1983/10/26 4.3. Click "Submit" button | System accepts and stores data in the correct format | Pass | Positive
23 |  | Verify Phone field accept different valid format | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter mandatory fields(F.Name:Dan, L.Name:Danish) 3.Enter Phone:(773)987-4321 4.3. Click "Submit" button | System accepts and stores data in the correct format | Pass | Negative
24 |  | Verify F.Name Filed does not accept 20+ characters | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter mandatory fields(F.Name:Dannnnnnnnnnnnnnnnnnn, L.Name:Danish) 3. Click "Submit" button | Error message appears "Contact validation failed: lastName: Path `firstName` (`Dannnnnnnnnnnnnnnnnnn`) is longer than the maximum allowed length (20)." | Pass | Negative/Boundary
25 |  | Verify L.Name Filed does not accept 20+ characters | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter mandatory fields (F.Name:Dan, L.Name:Danishhhhhhhhhhhhhhhhhhhh) 3. Click "Submit" button | Error message appears "Contact validation failed: lastName: Path `lastName` (`Danishhhhhhhhhhhhhhhhhhhh`) is longer than the maximum allowed length (20)." | Pass | Negative/Boundary
26 |  | Verify Email Filed can not accept invalid input | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter mandatory fields(F.Name:Dan, L.Name:Danish) 3.Enter Email: fakeemail.com 4. Click "Submit" button | Error message appears "Contact validation failed: email: Email is invalid" | Pass | Negative
27 |  | Verify Postal Code Filed can not accept invalid input | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter mandatory fields(F.Name:Dan, L.Name:Danish) 3.Enter Postal Code: 4578243 4. Click "Submit" button | Error message appears "Postal Code validation failed: Postal Code: Postal Code is invalid" | Fail | Negative
28 | Update Contact Info | User Update First and Last Name | Preconditions: Contact (Peter Smith) is created. User is on "Contact list" page. 1.Click on "Peter Smith" under Name tab 2.Verify user is at Contact Info page 3.Click on "Edit Contact" button 4.Update Fist Name field: Otto, Last Name field: Hess 5. Click on "Submit" button | Contact info updated | Pass | Positive
29 |  | Delete contact | Preconditions: Contact (Peter Smith) is created. User is on "Contact list" page. 1.Click on "Peter Smith" under Name tab 2.Verify user is at Contact Info page 3.Click on "Delte Contact" button 4.Pop-up window shows up "Are you sure you want to delete this contact?" 5. Click "Ok" | Contact is deleted. User is redirected to Contact list page | Pass | Positive | TRUE
30 |  | Delete contact-Cancel button functionality | Preconditions: Contact (Peter Smith) is created. User is on "Contact list" page. 1.Click on "Peter Smith" under Name tab 2.Verify user is at Contact Info page 3.Click on "Delte Contact" button 4.Pop-up window shows up "Are you sure you want to delete this contact?" 5. Click "Cancel" | Contact is not deleted. | Pass | Positive
31 |  | "Return to Contact List" Functionality | Preconditions: Contact (Peter Smith) is created. User is on "Contact list" page. 1.Click on "Peter Smith" under Name tab 2.Verify user is at Contact Info page 3.Click on "return to Contact List" button | User is redirected to Contact List page | Pass | Positive | TRUE

## Test Plan
TEST PLAN Project "Contact List"
INTRODUCTION | The test plan has been created to facilitate communication within the team members. The goal is to ensure that all functionalities work as expected, meet the requirements, and provide a smooth user experience. It includes the objectives,test responsabilities,enty and exit criteria,scope,schedule.
OBJECTIVE | Conduct testing of " Contact List" application to ensure its quality Create test documentation, work with test management and product management tools Work with API Automate manual TC
Project Information
TEST APPROACH/STRATEGY/METHODOLOGY | Agile/Scrum
Manual/API/Test Automation
IN SCOPE | This document mainly targets UI/API testing and validating data Functional (Exploratory,Smoke,Regression, E2E) Non-Functional(GUI,Compatibility,Usability) Backend(API,database)
OUT OF SCOPE | Performance, Accessibility
SCHEDULE
Tasks | Sprint 1 | Sprint 2
Create Test Case/Test suits based on requirements Reported software defects Create Test execution
Review API requrements,ceate request,collections Write API tests Automate Smoke tests
RISKS | Build is not ready Not enough resources(testers) Documentation is not up to date New/unexpected feature change
Resources
PEOPLE
Functional QA Egineer | Create and maintain QA documentation Perform testing(manual,API) Report defects, collaborate with developersto resolve issues Convert manual TC into Cucumber files Monitor TA results and fun failed ones manually
Test Automation Engineer | (Create and maintain TA scripts, run test scripts, report defects,do manual testing
TOOLS
Manual testing | Dev Tools, Postman,Newman
Test Automation | IntelliJ,Selenium Webdriver,Cucumber, ChroPath,GitHub
PROJECT/TEST MANAGEMENT | Google Drive, Google Sheets
ENVIRONMENT | https://thinking-tester-contact-list.herokuapp.com/ Browser:Windows(Chrome), Mac(Safari)
API BASE URL | https://thinking-tester-contact-list.herokuapp.com/
ENTER CRITERIA | Environment ready,build is stable
EXIT CRITERIA | 100% TC coverage 90-95% TC passed No bugs with P1 or P2 priority
ROLES AND RESPONSABILITIES
Project Manager | Acts as a primary contat for development and QA team. Responsible for project schedule and overall success of the project.
QA Lead | Participation in the project plan creation/update process. Planning and organization of the test process for the release. Cooridnate with QA engineers on any issues encountered during testing.
QA | Understand requirements. Writing and executing test cases. Preparing RTM. Defect reporting and tracking. Regression testing. Bug review meeting. Preparation for test data.

## BUG
UI
Bug# | Environment | Severity | Priority | Title | Bug Description | Steps to reproduce | Expected Result | Actual Result | Screenshot/Video | Notes
1 | OS & Browser : Windows 11, Chrome Version 132.0.6834.160 (Official Build) (64-bit) Device:Dell Inspirion 16 App version: N/A | Medium | High | No Confirmation Message After Successful Registration | After successfully completing the user registration process, the system does not display a confirmation message to inform the user that their registration was successful. | 1. Go to https://thinking-tester-contact-list.herokuapp.com/ 2. Verify page title "Contact List App" 3.Click on "Sign Up" button 4.Verify page title "Add User" 5.Enter valid user details (f.name(Test), l.name(Tester),email(majamkaran+123@gmail.com), password(ABC1234)) 6.Click "Submit" button | A confirmation message should be displayed stating "Registration successful. Please check your email for confirmation." | User is redirected to "Contact List" page. No confirmation message is displayed after successful registration. | https://drive.google.com/file/d/1_rq8FavTJuVP8ifCNJi71oMl-jggZUpe/view?usp=drive_link
2 | OS & Browser : Windows 11, Chrome Version 132.0.6834.160 (Official Build) (64-bit) Device:Dell Inspirion 16 App version: N/A | Medium | High | User Registration – Postal Code Field Accepts Invalid Input | The Postal Code field allows users to enter more than the expected 5 digits, which does not align with the validation rules. | Preconditions: User is logged in. 1.Click on "Add a New Contact" button 2. Enter mandatory fields(F.Name:Dan, L.Name:Danish) 3.Enter Postal Code: 4578243 4. Click "Submit" button | The system accepts invalid postal code input and allows form submission. | The system should display an error message and prevent submission when an invalid postal code is entered. | https://drive.google.com/file/d/1MjqTvfcJ9lOSapmKCsYzTrNZTHAQ1LyO/view?usp=drive_link https://drive.google.com/file/d/1leUlTy6BTLpnLL7ZfkRhxzkYNc3Q2spn/view?usp=drive_link
API
3 | Tool: Postman API Endpoint:https://thinking-tester-contact-list.herokuapp.com/contacts/ API Method:GET | Major | High | GET Contact API Returns List Instead of Specific Contact | API documentation missing endpoint to retrive a single contact info | Preconditions: Authentication token is available. At least one contact exists in the database. 1.Open Postman and set up a GET request to https://thinking-tester-contact-list.herokuapp.com/contacts/ 2.Add authentication 3.Send the request | The API should return only the contact with the specified contact_id. | The response contains a list of all contacts instead of the specific contact requested. | https://drive.google.com/file/d/1JxMJRsx6tbFdVhECi2UPz3o1T-57oHLh/view?usp=drive_link https://drive.google.com/file/d/1VFQxlfT7oFvzer1OVq0N0Ie8BFG4WBw5/view?usp=drive_link | The API documentation indicates that there should be an endpoint to retrieve a single contact using /contacts/{contact_id}, but it appears to be missing or not implemented correctly.
4 | Tool: Postman API Endpoint:https://thinking-tester-contact-list.herokuapp.com/contacts/ API Method:DELETE | Critical | High | DELETE Contact API Endpoint Missing in Documentation & Returns 503 Service Unavailable | The DELETE Contact API endpoint (DELETE /contacts/{contact_id}) is missing from the API documentation, making it unclear how the deletion functionality should be used. | Preconditions: Authentication token is available. At least one contact exists in the database. 1.Open Postman and set up a DELETE request to https://thinking-tester-contact-list.herokuapp.com/contacts/ 2.Add authentication 3.Send the request | The API should successfully delete the specified contact and return a 200 OK with "Contact deleted" message. | The API returns a 503 Service Unavailable error, indicating that the endpoint is either down or not implemented. | https://drive.google.com/file/d/1AjqCJELSfsbPH4cchHUPGz7ICOzl_LGi/view?usp=drive_link https://drive.google.com/file/d/1knJ2EJbQbO1ugeZbx0NhaXGKY5WbOzfQ/view?usp=drive_link | The DELETE endpoint is missing from the API documentation, making it difficult for users to understand its expected behavior. The API documentation should include a section for the DELETE /contacts/{contact_id} endpoint.
5 | Tool: Postman API Endpoint:https://thinking-tester-contact-list.herokuapp.com/contacts/ API Method:PUT | Critical | High | PUT Contact API Endpoint Missing in Documentation & Returns 503 Service Unavailable | The PUT Contact API endpoint (PUT /contacts/{contact_id}) is missing from the API documentation | Preconditions: Authentication token is available. At least one contact exists in the database. 1.Open Postman and set up a PUT request to https://thinking-tester-contact-list.herokuapp.com/contacts/ 2.Add authentication 3.Update contact first and last name in request body 4.Save and Send the request | The API should successfully update the specified contact and return a 200 OK. | The API returns a 503 Service Unavailable error, indicating that the endpoint is either down or not implemented. | https://drive.google.com/file/d/1MLmNUu3X4NsP-aDibaOvNud4FUXibUca/view?usp=drive_link https://drive.google.com/file/d/1qtyooldsO5_A89fToW9K4k55HucKhfT7/view?usp=drive_link | The API documentation should include a section for the PUT /contacts/{contact_id} endpoint.
6 | Tool: Postman API Endpoint:https://thinking-tester-contact-list.herokuapp.com/contacts/ API Method:PATCH | Critical | High | PATCH Contact API Endpoint Missing in Documentation & Returns 503 Service Unavailable | The PATCH Contact API endpoint (PATCH /contacts/{contact_id}) is missing from the API documentation | Preconditions: Authentication token is available. At least one contact exists in the database. 1.Open Postman and set up a PATCH request to https://thinking-tester-contact-list.herokuapp.com/contacts/ 2.Add authentication 3.Update contact password 4.Save and Send the request | The API should successfully update the specified contact and return a 200 OK. | The API returns a 503 Service Unavailable error, indicating that the endpoint is either down or not implemented. | https://drive.google.com/file/d/1wXeDTuZJBqFi1IyNblLl1IFZmFU5XUVD/view?usp=drive_link https://drive.google.com/file/d/1rXNhPb-P2MYUOY9Yynfiig6ib5sgq3TA/view?usp=drive_link | The API documentation should include a section for the PATCH /contacts/{contact_id} endpoint.